## Sheet1
Baghli-arabash | Status | Start date | End date | Actual start | Actual end | Percent complete
Homepage components:
1.1. Header
1.1.1. Website Logo
1.1.2. Wish list
1.1.3. Sign In
1.1.4. Register
1.1.5. About us
1.1.6. Translator Button |  | 2017-05-14 | 2017-05-14
1.1.6.1. Arabic | build and desgin
1.1.6.2. English
1.1.7. Search box |  | 2017-05-14 | 2017-05-15
1.1.7.1. All Categories
1.1.7.2. Specific category
1.1.7.3. Brand
1.1.8. Shopping Cart |  | 2017-05-16 | 2017-05-17
1.1.8.1. Number of items
1.1.8.2. Price
1.2. Main Menu
1.2.1. Home
1.2.2. Main Categories
1.2.2.1 X
1.2.2.2. Y
1.2.2.3. Z
1.2.2.4. Etc…
1.3. Stick icons |  | 2017-05-18 | 2017-05-18
1.3.1. Social Media links (Facebook, Twitter, Google + and Instagram).
1.4. Main Banner |  | 2017-05-18 | 2017-05-18
1.4.1. Images with/out URL (Internal / External)
1.4.2. Text for each and every image
1.5. Featured Products | Edit | 2017-05-21 | 2017-05-22
1.5.1. List of products sliding/fading effect;
1.5.1.1. Product image
1.5.1.2. Product name
1.5.1.3. Price after/before [If there is a discount]
1.6. New Arrival Products | Edit
1.6.1. List of products sliding/fading effect;
1.6.1.1. Product image
1.6.1.2. Product name
1.6.1.3. Price after/before [If there is a discount] | -
1.7. Most selling Products
1.7.1. List of products sliding/fading effect;
1.7.1.1. Product image
1.7.1.2. Product name
1.7.1.3. Price after/before [If there is a discount] | Edit
1.8. Tips & advices | Done
1.8.1. List of topics sliding/fading effect;
1.8.1.1. Topic image
1.8.1.2. Topic name
1.8.1.2.1. While click it will redirect the user to the details page of the topic.
1.8.2. See All [button]
1.8.2.1. While click it will redirect the user to the listing page of all the topics.
1.8.2.2. Tips/advertisements Videos as slider
1.9. Accepted Payments | Build | 2017-05-23 | 2017-05-23
1.9.1. Knet
1.9.2. Visa
1.9.3. MasterCard
1.10. Footer | Done
1.10.1. Sitemap
1.10.2. FAQ’s
1.10.3. Subscribe Newsletter
1.10.4. Privacy Policy
1.10.5. Social Media links (Facebook, Twitter, and Instagram).
1.10.6. Sitemap, About us, Contact us, FAQ’s, Tips & advices , Privacy Statement, Terms and Conditions (Quick links)
2.Sign In | Done
2.1. Email
2.2. Password
2.2.1. Stay Signed in (ticked by default)
2.2.2. Forgot your password?
2.2.2.1. While clicking it will redirect the user to reset password page, using the user email ID.
2.2.2.2. Proceed [Button]
2.2.2.2.1. Sending reset link to the user for reenter new password
2.3. Sign in [Button]
3. Register Page | Done
3.1. First name*
3.1. Last name*
3.2. Mobile number*
3.3. Password*
3.5. Re-enter Password*
3.6. Email*
3.7. Recovery Email*
3.7. Phone number
3.8. [Checkbox] I agree to Terms and conditions [while click it will redirect the user to terms and conditions page] [new tab]
3.9. [Checkbox] Subscribe to our Newsletter (ticked by default)
3.10. Register [Button]
3.10.1. Note: there is Buy as guest option so that the users can buy products without registering to the website
4. Wish list Page | Build and desgin | 2017-05-24 | 2017-05-24 | 21/5
4.1. Listing Page of products
4.1.1. Added while clicking on any products [Add to wish list] button.
4.1.2. There will be sorting by [Best Match, Most selling and Most rated] | not ready
4.2. Each product consists of;
4.2.1. Image
4.2.2. Name
4.2.3 Brand Name
4.3.4 Date [Added to wish list]
4.3.5 Delete[Button]
4.3.6 Choose Colour
4.3.7 Choose Size
4.2.8. Price after/before [If there is a discount]
4.2.9. Number of views
4.2.10. Rating [Stars] Number of votes
4.2.11.Free Shipping Text [If applicable]
4.2.12.Out of Stock Label[ If applicable]
4.2.13 Discount %
5. Shopping cart Page | Bulid and desgin | 2017-05-25 | 2017-05-28
5.1. Listing Page of products
5.1.1. Added while clicking on any products [Add to Cart] button.
5.1.2. Minimum Order Value
5.2. Each product consists of;
5.2.1. Image
5.2.2. Name
5.2.3. Small Description
5.2.3. Price after/before [If there is a discount]
5.2.4. Quantity
5.2.5. Discount % ( upper right)
5.2.6. Rating [Stars] Number of votes
5.2.7 Delete[Button]
5.2.8. Save for later [Button]
5.2.9 Total Price
5.3. Delivery Charge
5.4. Total Price after/before [If there is a discount]
5.5. Grand total Price [Final]
5.6. Buy All [Button]
5.6.1. While click it will redirect the user to review order page
5.6.2. Selecting exiting address or add new address.
5.6.3. Products review
5.6.3.1. Each product consists of;
5.6.3.1.1. Image
5.6.3.1.2. Name
5.6.3.1.3. Price after/before [If there is a discount]
5.6.3.1.4. Quantity
5.6.3.2. Delivery Charges
5.6.4. Place the order [Order has to exceed the minimum order value]
5.6.4.1. To redirect the user for payment
5.6.4.1.1. Knet
5.6.4.1.2. Visa
5.6.4.1.3. Master Card
5.6.4.2. After payment done;
5.6.4.2.1. If successful
5.6.4.2.1.1. Receipt will be issued with all the details of the order and status as [Successful]
5.6.4.2.2. If rejected
5.6.4.2.2.1. Receipt will be issued with all the details of the order and status as [Rejected]
6. List page for [Categories,Brand] Listing Page | Build and desgin | 2017-05-29 | 2017-05-30
6.1. Filter & sorting functionality based;
6.1.1. Products key words [text box] for searching in that specific list
6.1.2. Best Match | not ready
6.1.3. Newest | not ready
6.1.4. Most selling | not ready
6.1.5. Most rated | not ready
6.2. Each product consists of;
6.2.1. Product Image
6.2.2. Product Name
6.2.3 Brand Name
6.2.4 Choose Colour and Size
6.2.5. Price after/before [If there is a discount]
6.2.6 Quantity
6.2.7 Viewed Number | not ready
6.2.8. Free shipping text[If applicable]
6.2.9. Rating [Stars] Number of votes
6.2.10. Out of stock label [if the item is out of stock]
6.2.11 Add to cart [Button]
6.2.12 Add to wish list [Button]
6.2.13 Discount % ( upper right)
6.3. Pagination functionality [1,2,3,5, etc…]
6.4. Related Products
6.4.1. List of product marked as related to that specific list
6.4.1.1 Each product consists of;
6.4.1.1.1. Product Image
6.4.1.1.2. Product Name
6.4.1.1.3. Price after/before [If there is a discount]
7. Product details Page for [All the products] | done | 2017-03-31 | 2017-06-01 | 18/5 | 90%
7.1. Product directory starting from home page [Home > Category name > Product short name]
7.2. Product Images [Big Image and slider for small images]
7.3. Product Name
7.3. Product Small description
7.4 Brand Name
7.4. Rating [Stars] Number of votes
7.5. Number of orders
7.6. Price
7.7 Before Price
7.8 Free Shipping Text
7.7. Discount Price [If there is a discount]
7.8. Quantity
7.9 Choose colour and size
7.9. Out of stock label [if the item is out of stock]
7.9.1. In that case add to cart button will be disable and instead of it will add one button for notify the user once the item come to stock.
7.9.2. If the user click on notify me system will check if the user is already signed in system will give a pop telling the user that we will send you notification once the item back to stock
7.9.3. If the user not signed in system will redirect the user to login page to sign in or register .
7.10 Add to Cart [Button]
7.11 Add to Wish list [Button]
7.12 Buy Now [Button]
7.13. Product Details
7.13.1. Product Description
7.13.2. Photo Gallery
7.13.3. Video Gallery
7.13.4. Tips & Advices for that specific item
7.13.5. Available colors and sizes for the same corresponding product (if any)
7.14. Like button [user can click on that button to like the item and the system will calculating the numbers and display it in the page.
7.15. Customers Reviews [How many review]
7.15.1. Name of Customer
7.15.2. Order information
7.15.3. Review text
7.15.4. Number of stars voted
7.16. Related Products
7.16.1. List of product marked as related to that specific list
7.16.1.1.1. Each product consists of;
7.16.1.1.1. Product Image
7.16.1.1.2. Product Name
7.16.1.1.3. Price after/before [If there is a discount]
7.17. You May also like
7.17.1. List of product marked as related to this specific product
7.17.1.1 Each product consists of;
7.17.1.1.1. Product Image
7.17.1.1.2. Product Name
7.17.1.1.3. Price after/before [If there is a discount]
8. User Profile Page | Bulid and desgin
8.1. Account Dash board |  | 2017-06-04 | 2017-06-06
8.1.1. Hello Full name
8.1.2. Personal information
8.1.2.1. Full Name
8.1.2.2. Email
8.1.2.3. Mobile number
8.1.2.4. Phone number
8.1.3. Delivery Address [Default]
8.1.3.1. Address Name
8.1.3.2. Address Information
8.1.3.3. Phone number
8.2. Manage Information
8.2.1. Personal Information
8.2.1.1. First Name
8.2.1.2. Last Name
8.2.1.3. Mobile number
8.2.1.4. Phone number
8.2.1.5. Email
8.2.1.6. Delivery Address [Default]
8.2.1.6.1. Address Name *
8.2.1.6.4. Area*
8.2.1.6.4. Block*
8.2.1.6.5. Street*
8.2.1.6.6. Avenue
8.2.1.6.7. Building Number*
8.2.1.6.8. Floor Number
8.2.1.6.9. Flat Number
8.2.1.6.10.Comments
8.3. Addresses book
8.3.1. Delivery Address [Default]
8.3.1.1. Address Name *
8.3.1.2. Area*
8.3.1.4. Block*
8.3.1.5. Street*
8.3.1.6. Avenue
8.3.1.7. Building Number*
8.3.1.8. Floor Number
8.3.1.9. Flat Number
8.3.2. Add New address
8.3.3. Set specific address as default functionality.
8.4. Orders
8.4.1. Listing page of Open orders and Previous Orders
8.4.2. Sorting by [Order Status]
8.4.2.1. Each product consists of;
8.4.2.1.1. Order ID
8.4.2.1.2. Order Time & Date
8.4.2.1.3. Order status [Ongoing-Completed]
8.4.2.1.4. Order Amount
8.4.2.1.5. During [Value of days] user can give the following for the completed Orders
8.4.2.1.5.1. Giving Votes [Stars]
8.4.2.1.5.2. Giving Review
8.5. Change password
8.5.1. Current password*
8.5.2. New Password*
8.5.3. Confirm New Password*
1.1.1. Social Media links (Facebook, Twitter, and Instagram).
1.1.2. Sitemap, About us, Contact us, FAQ’s, Tips & advices, Privacy Statements, Terms & Conditions(Quick links)
9. FAQ’s Page | desgin | 2017-06-07 | 2017-06-08
9.1. Page for all the questions and answers related to website.
10. About Us Page
10.1. Corporate Overview | done |  |  |  | 100%
11. Contact Us Page | done |  |  |  | 100%
11.1. Contact / Address information / Location on Map / Hotline
11.1.1 Call no. should be clickable which will show on mobile to call
11.1.2 Comments should not have limitation
11.1.3 Once submit it should show " Thank you for contacting Us , we will contact you in
11.2. Feedback/ Inquiry form
11.2.1. Name
11.2.2. Email
11.2.3. Phone Number
11.2.4. Other Number(optional)
11.2.4. Text Box (details)
Adminestration
- Customer List
- Order Tracking
-Report
Depending on Comments in SRS there are more comments to work , however we sent previous break down and it get the approval … I wanna add new tasks in break down
12. General Comments
12.1. Special Request form for requesting a product that is not found on the website. It can also have attachments
12.2. Advt. management: This will show related products on each product detailed page.
12.3. Later the admin can make offers or discounts to a certain category specifically
12.4. Admin can make discount option for Products.
12.5. Admin can block the fake customer
12.6 If the user searches for something and he finds it out of stock, then there should be a button appearing for the user: “Request this item” so he can send to the admin telling him I need this, get it for me. User (Registered/ guest) can request this item. Guest User will fill contact details also. When the admin has stock, he can know who requested it and contact him.
12.7. For good customer/purchased high amount or recommended website, admin can mark it as VIP customer and can give special offer.
12.8.Email notifications: the user will receive email notifications for every step
12.8.1 Register
12.8.2 Place new order + Order payment receipt (after delivery & payment)
12.8.3 Change in Profile (Password Change)
12.9. VIP Customer Functionality
12.9.1 Requesting list of all Customers with total purchased amount above (X amount) that will be defined by admin
12.9.2 Admin have the privilege to add VIP flag for them all.
13.1 Service Rating Survey
13.1.1 Once customer order delivered to him and the status of deliver “Completed” in the system, system will send a small survey to rate the service
13.2 Google Analytic Integration
13.2.1 Integrate Google Analytics in Website
13.3 Administrator- Customer List
13.3.1 Address can be managed from Admin Area
13.3.2 Customers can be added for newsletter subscription Ability to send email shot for:
13.3.2.1 VIP subscribed customers only
13.3.2.2 Normal subscribed Customers
13.3.2.3 All subscribed Customers
13.4 Disabled users are listed in red like the following screen shot
13.5 BESTSELLER
13.5.1 Best seller will list all product assigned in best seller area
13.5.2 This will list all orders received in this system
13.5.3 All these orders can be exported to Excel
13.5.4 Status can be added to all orders like pending, Processing , Delivered and Rejected
13.5.5 On clicking each order, admin can find order details
13.5.6 Once payment status is successful, order quantity will be removed from stock using web services.
Administrator- Report
13.6 Sales Report
13.6.1 This report will display the sales for all products in system
13.6.2 The report can be generated for :
13.6.2.1 selected product name
13.6.2.2 Selected category
13.6.2.3 Or all
13.6.3 The report can be generated for selected period :
13.6.3.1 Daily: admin can select the day he would like to get the report for it
13.6.3.2 Weekly
13.6.3.2.1 Select Year
13.6.3.2.2 Select month
13.6.3.2.3 Select week by choosing the period of the week or (1st week, 2nd week,..etc)  one of options will be applied
13.6.3.2.4 The admin will get report of selected/all products within selected week/period
13.6.3.2.5 Ability to select more than week and the result will show in the same report (for comparison purpose), each week will have list of most sold products
13.6.3.2.6 report should categories the result of product list based on created categories in the system
13.6.3.3 Monthly
13.6.3.3.1 Select Year
13.6.3.3.2 Select month
13.6.3.3.3 admin will get list of selected/all products within selected month
13.6.3.3.4 Ability to select more than one month and the result will show in the same report (for comparison purpose) Report should categories the result of product list based on created categories in the system
13.6.3.4 Yearly
13.6.3.4.1 Select Year
13.6.3.4.2 admin will get list of selected/all products within selected Year
13.6.3.4.3 Ability to select more than one year and the result will show in the same report (for comparison purpose)  this will be based on the information saved in the database for the previous years (if any)
13.7 Subscriber Report
13.7.1 This report will list all customer subscribed and created account in the system Only with the following information
13.7.2 The list should contain both (VIP /normal ) Customers
13.7.3 Admin have the ability to request report for :
13.7.3.1 All subscribed customers
13.7.3.2 VIP subscribed customers
13.7.3.3 Normal subscribed customers
13.8 Search Report
This report will give the list of keywords used in website for searching product. Report will be based on Period
13.8.1 Today
13.8.2 Last Month
13.8.3 Last 7 Days
13.8.4 Yesterday
13.8.5 Last 24 Hours
13.8.6 This month
13.8.7 This Year
13.8.8 Custom – Specifying From date and To Date
13.9 Payment Report
This report will give the list of payments received through shopping cart. Report will be based on Period
13.9.1 Today
13.9.2 Last Month
13.9.3 Last 7 Days
13.9.4 Yesterday
13.9.5 Last 24 Hours
13.9.6 This month
13.9.7 This Year
13.9.8 Custom – Specifying From date and To Date
13.9.9 per product, per brand, per category
14 Stock Availability Report
This report will be display only for the day admin use the function to request this report
The result will be for :
14.1 Either for selected category
14.2 Or selected product name
14.1 Or for all
15 Top Sellers Report
The top selling products will be counted based on most purchased product
The report should display the top 100 seller in following format as example:
The above table will be displayed based on selected period :
15.1 Daily: admin can select the day he would like to get the report for
15.2 Weekly:
15.2.1 Select Year
15.2.2 Select month
15.2.3 Select week by choosing the period of the week or (1st week, 2nd week,etc)  one of options will be applied
15.2.3 The admin will get the report for listed top 100 seller product within selected week/period
15.2.4 Ability to select more than week and the result will show in the same report (for comparison purpose), each week will have list of most viewed products
15.2.5 report should categories the result of product list based on created categories in the system
15.3 Monthly:
15.3.1 Select Year
15.3.2 Select month
15.3.3 admin will get list of top 100 seller product within selected month
15.3.4 Ability to select more than one month and the result will show in the same report (for comparison purpose)
15.3.5 report should categories the result of product list based on created categories in the system
15.4 Yearly:
15.4.1 Select Year
15.4.2 admin will get list of top 100 seller product within selected Year
15.4.3 Ability to select more than one year and the result will show in the same report (for comparison purpose)  this will be based on the information saved in the database for the previous years (if any)
15.4.4 report should categories the result of product list based on created categories in the system
16 Top Ordered Customer Report
Top order customers as value and as number of transaction. Comparison by
16.1 Weekly
16.2 Monthly
16.3 Yearly
17 Most Viewed Products Report
The view will be counted based on Click on Product to view the detail page of each product regardless if customer purchased or not the product
The report should display the most 100 viewed products based on :
17.1 Daily: admin can select the day he would like to get the report for
17.2 Weekly:
17.2.1 Select Year
17.2.2 Select month
17.2.3 Select week by choosing the period of the week or (1st week, 2nd week,etc)  one of options will be applied
17.2.3 The admin will get the report for listed top 100 seller product within selected week/period
17.2.4 Ability to select more than week and the result will show in the same report (for comparison purpose), each week will have list of most viewed products
17.2.5 report should categories the result of product list based on created categories in the system
17.2.6 The report should show the quantity sold of the product at the same period.
17.3 Monthly:
17.3.1 Select Year
17.3.2 Select month
17.3.3 Admin will get list of 100 viewed product within selected month
17.3.4 Ability to select more than one month and the result will show in the same report (for comparison purpose)
17.3.5 report should categories the result of product list based on created categories in the system
17.3.6 The report should show the quantity sold of the product at the same period.
17.4 Yearly:
17.4.1 Select Year
17.4.2 admin will get list of top 100 seller product within selected Year
17.4.3 Ability to select more than one year and the result will show in the same report (for comparison purpose)  this will be based on the information saved in the database for the previous years (if any)
17.4.5 report should categories the result of product list based on created categories in the system
17.4.6 The report should show the quantity sold of the product at the same period.
18 Survey Report
Report based on the surveys submitted by customers
18.1 Today
18.2 Last Month
18.3 Last 7 Days
18.4 Yesterday
18.5 Last 24 Hours
18.6 This month
18.7 This Year
18.8 Custom – Specifying From date and To Date
18.9 Last 30 Days
19 VIP Report
Report should show VIP customers, who have frequently purchased products from the site/ purchased above a fixed rate. |  |  |  | from the site/ purchased above a fixed rate.
19.1 Today
19.2 Last Month
19.3 Last 7 Days
19.4 Yesterday
19.5 Last 24 Hours
19.6 This month
19.7 This Year
19.8 Custom – Specifying From date and To Date
19.9 Last 30 Days
20 Most Rated Product Report
20.1 Display top 100 rated products
20.2 List will display products as per their category list
20.3 Number of customers rated the product
20.4 The rating will be up to now only (the day which admin request the report from the system)
21 Customers Total Order Report
list of customers totals list by :
List of customers total orders within
21.1 A day
21.2 A Selected week
21.3 A Selected month
21.4 A Selected year
21.5 Most order Customer in value
22 Survey Report
List of customers survey details with
22.1 Survey Answers
22.2 Total Results
22.3 Comments
Note : Admin should be able to export all above reports in Excel format
User- Export
All Users registered in this cart can be exported to excel format
CHANGE REQUEST
1- Solve product quantity if the requested quantity greater than actual quantity | 1 day
2-contact us page : put numbers and words in a good position , put the number of price as a float number and add currency at the final .
3- Add Search in home page that search for any keyword put in the input . | 2 hours
4- give full name for the product when hover over it . | half hour
5- modify categories as a group and make sub-category with products . | 4 days